## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 14.03. - 28.03.
Group Number |  | 6
Participant 1 |  | Laura Engleitner
Participant 2 |  | Alexander Nachtmann
Participant 3 |  | Stephanie Rauscher
Participant 4 |  | Benjamin Storck
Participant 5 |  | Tamara Wilhelm
Mentor |  | Lukas Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
PION-8 | html & bootstrap | 0.5 | 0.25 | -0.25 | x |  | commiten hat am längsten gedauert
PION-12 | navbar | 1 | 0.75 | -0.25 | x
PION-9 | layout skizze 1.Frau | 2 | 3 | 1 | x |  | kann nicht zeichnen, hab einfach html benutzt, ref github .png ansehen
PION-58 | scroll ideen, mit quellen | 2 | 3 | 1 | x |  | hab den html code aus pion-9 benutzt um features zu zeigen,github code->quellen
PION-54 | Look and Feel | 3 | 3.5 | 0.5 | x
PION-57 | Techerche Scrollytelling | 2 | 3 | 1 | x |  | Ziel/DoD für diese Story nicht ausreichend definiert
PION-10 | Recherche Ada Lovelace | 3 | 3.5 | 0.5 | x |  | sichergehen dass valide quellen benutzt werden und auf plagiatsfreiheit achten hat am längsten gedauert
PION-56 | Recherche zu Websites und Quellen | 1 | 1 | 0 | x
PION-24 | Quellenverzeichnis zur Recherche | 0.5 | 0.5 | 0 | x
PION-55 | Bootstrap CDN | 0.25 | 0.25 | 0 | x |  | bootstrap 4 für jetzt
10 |  | 15.25 | 18.75 | 3.5 | 10 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol