## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 03.05. - 16.05.23
Group Number |  | 6
Participant 1 |  | Laura Engleitner
Participant 2 |  | Alexander Nachtmann
Participant 3 |  | Stephanie Rauscher
Participant 4 |  | Benjamin Storck
Participant 5 |  | Tamara Wilhelm
Mentor |  | Lukas Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
PION-73 | Portrait layout template | 0 | 2 | 2 | x
PION-88 | single image layout template | 1 | 3 | 2 | x
PION-90 | single-choice fragen-layout | 3 | 3 | 0 | x |  | .js auch dabei
PION-91 | single-choice antwort-layout | 1 | 1 | 0 | x
PION-92 | multiple-choice | 3 | 6 | 3 | x |  | .js auch dabei
PION-87 | textbox | 3 | 3.5 | 0.5 | x
PION-11 | bildmaterial | 1 | 1 | 0 | x |  | Ordner hochladen auf Confluence nicht mögl.
PION-64 | 5. Pionierin | 2 | 2 | 0 | x
8 |  | 14 | 21.5 | 7.5 | 8 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol