## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 29.03. - 17.04.2023
Group Number |  | 6
Participant 1 |  | Laura Engleitner
Participant 2 |  | Alexander Nachtmann
Participant 3 |  | Stephanie Rauscher
Participant 4 |  | Benjamin Storck
Participant 5 |  | Tamara Wilhelm
Mentor |  | Lukas Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
PION-48 | Layout | 5 | 8.5 | 3.5 | X |  | 0,5 Überlegungen zu Frameworks & Templates
PION-61 | short info for modul 1 | 2 | 2 | 0 | X
2 |  | 7 | 10.5 | 3.5 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol