## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 18.04. - 02.05.23
Group Number |  | 6
Participant 1 |  | Laura Engleitner
Participant 2 |  | Alexander Nachtmann
Participant 3 |  | Stephanie Rauscher
Participant 4 |  | Benjamin Storck
Participant 5 |  | Tamara Wilhelm
Mentor |  | Lukas Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
PION-78 | Layout | 5 | 8.5 | 3.5 | X
PION-78 | 10 Quizfragen Radia Perlman | 1 | 1 | 0 | X
PION-79 | 10 Quizfragen Grace Hopper | 1 | 1 | 0 | X
PION-80 | 10 Quizfragen Ada Lovelace | 1 | 1 | 0 | X
PION-82 | share-button android & ios | 1 | 1 | 0 | X
PION-83 | bootstrap-share-icon | 0.1 | 0,05 | -0.5 | X
PION-62 | Infos über Grace Hopper | 2 | 2 | 0 | X
PION-63 | Infos über Karen Späck Jones | 2 | 2 | 0 | X
PION-84 | 10 Antworten zu Radia Perlman’s Quizfragen | 1 | 1 | 0 | X
PION-85 | 10 Antworten zu Grace Hopper’s Quizfragen | 1 | 1 | 0 | X
PION-86 | 10 Antworten zu Ada Lovelace’s Quizfragen | 1 | 1 | 0 | X
PION-74 | Bootstrap ändern | 0.2 | 0.2 | 0 | X
PION-73 | Portrait Komponente | 1 | 5 | 4 |  | X | needs rework for responsive
13 |  | 17.3 | 13.5 | 7 | 12 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol