## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 16.05.23 - 30.05.23
Group Number |  | 6
Participant 1 |  | Laura Engleitner
Participant 2 |  | Alexander Nachtmann
Participant 3 |  | Stephanie Rauscher
Participant 4 |  | Benjamin Storck
Participant 5 |  | Tamara Wilhelm
Mentor |  | Lukas Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
PION-98 | Scroll Frameworks suchen | 3 | 3 | 0 | x |  | animate on scroll oder lax.js
PION-47 | Quizfragen-Tabelle DB | 3 | 6 | 3 | x |  | Es ist schwierig, den tatsächlichen Aufwand zu bestimmen, da ich eine Datenbank für XAMPP, die FH-Seite und eine kostenlose Sub-Domain erstellen musste. Ich war mir nicht sicher, ob die FH einen kostenlosen Service mit PHP/MySQL anbietet. Die Ausführung des MySQL-Befehls dauerte nicht lange, aber der Rest fühlte sich an wie 6 Stunden.
PION-94 | Quizantworten-Tabelle DB | 2 | 2 | 0 | x
PION-95 | Top-3 Tabelle | 1 | 4 | 3 |  | x | in Sprint 6 verbessern -- nicht zufrieden. php frustriert.
PION-104 | Webhost eingerichtet | 1,5 | 3 | 1.5 | x |  | Die E-Mail-Kommunikation, die Auseinandersetzung mit dem Admin-Tool und Probleme mit dem VPN am Anfang, sowie der Start und Upload rechtfertigen den tatsächlichen Aufwand
PION-105 | Überarbeitung der Quiz-Logik in js | 2,5 | 2,5 | 0 | x
PION-13 | Text Ada Lovelace | 2 | 2 | 0 | x
PION-38 | Text Ada Lovelace | 2 | 2 | 0 | x
PION-93 | Scroll Frameworks suchen | 3 | 5 | 2 | x |  | CSS Transformations, CSS Animations, Parallax Scrolling, ect
PION-41 | Scroll navigation | 4 | 4,5 | 0.5 |  | x | muss noch mal angeschaut werden
PION-95 | Quiz Belohnungssystem | 1 | 1 | 0 |  | x | muss noch mal angeschaut werden
11 |  | 25 | 35 | 10 | 8 | 3
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol