## Tabelle1
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 30.05. - 13.05.2023
Group Number |  | 6
Participant 1 |  | Laura Engleitner
Participant 2 |  | Alexander Nachtmann
Participant 3 |  | Stephanie Rauscher
Participant 4 |  | Benjamin Storck
Participant 5 |  | (Tamara Wilhelm)* |  |  |  |  | * Im Laufe des Sprints hat Tamara uns mitgeteilt, dass sie das Studium abbrechen wird
Mentor |  | Lukas Aichbauer
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
PION-107 | intro text and layout | 1 | 3.5 | 2.5 | x |  | svg responsive was painful
PION-117 | intro animation | 1 | 1.5 | 0.5 | x
PION-118 | Layout Frage + Text+ antwortbox mit layout und text | 1 | 4.5 | 3.5 | x |  | Css manuell couldnt do it otherwise
PION-121 | multchoice layout | 2 | 6 | 4 | x |  | css for each quiz modul single+mult in 1 css
PION-122 | multquiz logik adjustment Modul 1+2 | 2 | 2 | 0 | x
PION-123 | singlequiz feedback Modul 1+2 | 2 | 2 | 0 | x
PION-124 | multquiz richtig/falsch Modul 1+2 | 2 | 2 | 0 | x
PION-125 | singlequiz feedback Modul 1+2 | 2 | 2 | 0 | x
PION-126 | multquiz feedback Modul 1+2 | 2 | 2 | 0 | x
PION-127 | singlequiz feedback Modul 1+2 | 2 | 2 | 0 | x
PION-120 | single choice js | 1.5 | 4 | 2,5 | x |  | every quiz modul has combined single+mult logik
PION-119 | mult choice js | 1.5 | 4 | 2.5 | x
PION-129 | mult choice button lock | 0.1 | 0.1 | 0 | x
PION-130 | Modularity Quiz | 3 | 6 | 3 | x
PION-128 | single choice button lock | 1 | 1 | 0.5 | x
PION-132 | bug fix | 2 | 2 | 0 | x |  | siehe github/discord
PION-99 | whole module | 5 | 7.5 | 2.5 | x
PION-41 | reibungslose Navigation | 4 | 4.5 | 0.5 | x
PION-100 | Scroll-Animation Portrait | 2 | 2 | 0 | x
PION-101 | Scroll-Animation Text | 1 | 1 | 0 | x
PION-102 | Scroll-Animation Bild | 1 | 0.5 | -0.5 | x
PION-103 | Scroll-Animation Single Choice | 1 | 0.5 | -0.5 | x
PION-116 | Navigationsleiste stylen/funktion | 2 | 3 | 1 | x |  | idee mit freischalten nach quiz verworfen
PION-39 | Quellen anzeigen | 1 | 1 | 0 | x
PION-95 | Quizz-Belohnungssystem | 1 | 2 | 1 |  | x | nicht weiter verfolgt
PION-109 | Modul 2 ganz | 7 | 1.5 | -5.5 |  | x
PION-81 | Share Button implementieren | 1 | ? | ? |  | x
PION-36 | Impressum | 2 | ? | ? |  | x
27 |  | 53.1 | 68.1 | 15 | 24 | 3
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol